## Sheet1
Tasks | Estimated hours | Sprint 1 - number of hours spend | Sprint 2 - number of hours spend | Sprint 3 - number of hours spend | Sprint 4 - number of hours spend | Sprint 5 - number of hours spend | Total hours
Planning | 2 | 2.3 | 0 | 0 | 0 | 0 | 2.3
Requirements | 4 | 1 | 0 | 0 | 0 | 0 | 1
Conceptual diagram | 64 | 40 | 18 | 0 | 0 | 0 | 58
Class diagram | 12 | 0 | 20 | 0 | 0 | 0 | 20
Time schedule | 1 | 0 | 0.5 | 0 | 0 | 0 | 0.5
Burndown Chart | 1 | 0 | 0.5 | 0 | 0 | 0 | 0.5
Implementation | 20 | 0 | 0 | 5 | 5 | 0 | 10
Testing | 20 | 0 | 0 | 5 | 5 | 0 | 10
Documentation | 8 | 0 | 0 | 0 | 4 | 0 | 4
Presentation | 8 | 0 | 0 | 0 | 0 | 1 | 1
Actual remaining hours | 140 | 96.7 | 57.7 | 47.7 | 33.7 | 0
Estimated remaining hours | 140 | 112 | 84 | 56 | 28 | 0